## Sheet1
SL.NO | Description | Description | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Install and set python and langchain environment. | Sprint 1 | Backend Team | Setup Issue | Installed Python 3.12, created virtual environment, installed LangChain + dependencies | 17.11.2025 | Closed | Environment ready
2 | LLM connection failing due to incorrect API key setup | Sprint 1 | Backend Team | Integration | Configured correct API key & environment variables | 20.11.2025 | Closed | Tested successfully
3 | Agent not returning valid response for some prompts | Sprint 2 | Backend Team | Functional | Updated prompt template & agent logic | 21.11.2025 | Closed | Verified
4 | Tool-enabled agent returned invalid JSON output | Sprint 3 | Backend Team | Integration | Added JSON validation + schema handling | 26.11.2025 | Closed | Stable now
5 | Shared memory not storing full chat history | Sprint 3 | Backend Team | Memory | Reconfigured memory persistence & retested | 19.12.2025 | Closed | Working correctly
6 | Multi-agent routing incorrect for some tasks | Sprint 4 | Backend Team | Logical | Improved agent role assignment logic | 29.12.2025 | Closed | Optimized
7 | UI failed to refresh chat messages instantly | Sprint 4 | Frontend Team | UI/UX | Updated refresh trigger | 31.12.2025 | Closed | Verified